## Inventory_Location_Transfer
Defect_ Id | Date | Status | Project Name | Module Name | Sub - Module Name | Severity | Priority | Type | Phase | Summary | Steps to Reproduce | Test Data | Expected Result | Actual Result | Reported By | Assigned to | Screen shots
D_001 | 25th May 2021 | New | Front Accounting | Items and Inventory | Inventory Location Transfer | High |  | Functional | System Testing | While transfering Inventory, Error message as "Reference number is already in use" is displayed | Select From Location | Thane - Ghodbundar Rd. Nr. Raheja Complex | Data should be displayed in From Location text field | Data is displayed in From Location text field | Miss. Pallavi Natle
[11 empty] | Select To Location | MBP - Ghansoli | Data should be displayed in To Location text field | Data is displayed in To Location text field
[11 empty] | Select the Item | Apple MacBook Air Core i5 | Data should be displayed in Item text field | Data is displayed in Item text field
[11 empty] | Enter the Quantity | 1 | Data should be displayed in Quantity text field | Data is displayed in Quantity text field
[11 empty] | Click on Add Item button |  | Item should be added | Item is added
[11 empty] | Enter Memo | Transfer of Apple MacBook | Data should be displayed in Memo text field | Data is displayed in Memo text field
[11 empty] | Click on Process Transfer button |  | Notification as "transfer Processed successfully" should be displayed. Transfer should be processed sucessfully. Location Transfer no. should be provided | Error message as "Reference number is already in use" is displayed. Transfer is not processed.
D_002 | 25th May 2021 | New | Front Accounting | Items and Inventory | Inventory Location Transfer | High |  | Functional | System Testing | After successfully processed Inventory transfer , Location Transfer number is not provided | Select From Location | Nerul | Data should be displayed in From Location text field | Data is displayed in From Location text field | Miss. Pallavi Natle
[11 empty] | Select To Location | Pune - Karve Road - Godown | Data should be displayed in To Location text field | Data is displayed in To Location text field
[11 empty] | Select the Item | Apple MacBook Air Core i5 | Data should be displayed in Item text field | Data is displayed in Item text field
[11 empty] | Enter the Quantity | 51 | Data should be displayed in Quantity text field | Data is displayed in Quantity text field
[11 empty] | Click on Add Item button |  | Item should be added | Item is added
[11 empty] | Enter Memo | Transfer of Apple MacBook | Data should be displayed in Memo text field | Data is displayed in Memo text field
[11 empty] | Click on Process Transfer button |  | Notification as "transfer Processed successfully" should be displayed. Transfer should be processed sucessfully. Location Transfer no. should be provided | Notification as "Inventory transfer has been processed " is displayed. Transfer is processed sucessfully. Location Transfer no. is not provided